## Slide 1: Monitor and Evaluate Policy Advocacy

## Slide 2: Step 8: Develop Monitoring and Evaluation Plan
Purpose: demonstrate progress toward your goals and objectives and define success for advocacy strategy
Consider the factors that make M&E of advocacy different
Decide on methods for collecting data and measuring success
Develop indicators for your advocacy strategy

## Slide 3: Monitoring and Evaluation Basics Common M&E Terms
  Goals
  Objectives
  Indicators
  Targets
  Data/collection methods
  Logic model
  Inputs
  Activities
  Outputs
  Outcomes
  Impact
  Performance monitoring plan (PMP)

## Slide 4: “M” in M&E
Monitoring is the systematic process of collecting, analyzing, and using information/ data on specified project indicators to:
  Track progress of project implementation
  Track progress to reaching objectives
  Account for the use of allocated funds
  Guide management decisions
The information is used by project staff, management, and stakeholders.

## Slide 5: “E” in M&E
Evaluation is the systematic collection and analysis of information about the characteristics and outcomes of programs to:
  Make judgments, improve effectiveness, and inform decisions about current and future programming
  Compare expected and achieved results
  Examine contextual factors and causality to understand achievements or lack of achievement
Involves measuring changes in knowledge, attitudes, behaviors, skills, community norms, and use of services at the program or population level

## Slide 6: Basic Logic Model Structure
Resources/ Inputs
Activities
Outputs
Outcomes
Impact
1
2
3
4
5
Your Planned Work
Your Intended Results

## Slide 7: Logic Model Example—A Wedding
Inputs
Couple
Budget
Venue
Family and friends
Vendors
Activities
Hire Vendors
Write vows
Get married
Celebrate with friends and family
Go on a honeymoon
Outputs
600 photos taken
1 marriage certificate signed
200 guests fed
2 vows exchanged
75 gifts received
Outcomes
Couple:
Is married
Enjoyed time with family and friends
Had fun on their special day
Impact
Stronger family bonds for couple
Stronger family bonds for the families

## Slide 8: Indicators
M&E requires the use of indicators.
Indicators define the data that you are collecting.
  Example: number of people sensitized on GBV and GBV services
An indicator is a variable (its value changes) that measures the components of a program or project (inputs, activities, outputs, outcomes ).
Indicators can be quantitative or qualitative.

## Slide 9: Characteristics of Good Indicators
Valid: accurate measure of a behavior, practice, or task that is the expected output or outcome of the activity
Precise: operationally defined in clear terms
Measurable: quantifiable using available tools and methods
Reliable: consistently measurable in the same way by different observers

## Slide 10: Characteristics of Good Indicators (continued)
Comparable: can be measured in different contexts or time periods
Time-bound: requires completion by a specific date
Programmatically important: Why do we want to know this? Is the information useful?

## Slide 11: Monitoring & Evaluation for Advocacy Work
Routine tracking of inputs and outputs
Measuring the changes resulting from program activities over time
Evaluation
Is the advocacy strategy being executed according to plan and on budget?
Are the activities still appropriate given external changes?
Is the advocacy having the intended effect on target audiences?
What are the successes and failures?
What is happening that you didn’t expect?
Source: Building on the Easy Wins: A Framework for Planning and Evaluating Proactive Long-Term Policy Advocacy. Health Policy Project; 2016.
Monitoring

## Slide 12: Types of Indicators for M&E of Advocacy
Process/output indicators: numbers/types of activities and quality determinants—what you will do and how you will do it
  Example: X different organizations contacted to participate in the coalition using best practices in engagement.
Interim outcome indicators: how you will know that attitudes, knowledge, and behavior of target audiences and allies have changed in the short and medium terms
  Example: X new partners have shared coalition-approved messages with targets.
Long-term outcome indicators: the policy change for which you have advocated
  Example: The local council approved policy change X with 85 percent of our preferred policy elements.
Source: Building on the Easy Wins: A Framework for Planning and Evaluating Proactive Long-Term Policy Advocacy, Health Policy Project, 2016.

## Slide 13: Logic Model with Sample Indicators
Funding
Staff
Plans
Training materials
- Policy review
- Engage new partners in coalition
- Conduct community dialogues
- Health provider sensitization trainings
- Partners engaged in coalition
- Community dialogue held; topics listed
- Providers trained and scored on attitudes
- New partners actively sharing coalition messages
- Positive feedback from dialogues
- Improved attitude of providers
- Friendly services
Enabling environment increases access and use of services by PLHIV
Inputs
Activities
Outputs
Outcomes
Impact
Indicators:
# of partners contacted
# of partners engaged in coalition
# of new partners sharing messages of the coalition
# of PLHIV accessing services

## Slide 14: Distinctive Features of Advocacy M&E
Time frames can be unpredictable
Strategies and milestones shift
Assessing progress and interim outcomes is important; not just impact
Context may define progress and outcomes
Demonstrate contribution to results, not simply attribution
Source: Advocacy Toolkit, UNICEF, 2010.

## Slide 15: Methods to Evaluate Advocacy
Traditional
Interviews
Case studies
Surveys
Focus groups
Polling
Event observation
Unique
Bellwether methodology
Intense period debriefs
Critical incident timelines
Systems mapping
Policymaker ratings
Champion tracking
Media scorecards
360-degree critical incident reviews
Research panels
Social media tracking
Intercept interviews
Rapid response research
Source: Building on the Easy Wins: A Framework for Planning and Evaluating Proactive Long-Term Policy Advocacy. Health Policy Project; 2016.

## Slide 16: Method: Policymaker Ratings
Support
1=Not at all supportive
2=Interested
3=Somewhat supportive
4=Supportive
5=Extremely supportive
1=Not very influential
2=Somewhat influential
3=Influential
4=Extremely influential
1=Not very confident in the rating
2=Somewhat confident
3=Extremely confident
NOTE: You must identify observable characteristics or behaviors that differentiate each “level” on the scale for consistency between raters and ratings.
Influence
Confidence
Developed by: Julia Coffman, Harvard Family Research Project.

## Slide 17: Method: Systems Mapping
Step 1
Step 2
Step 3
Useful when trying to track systems change
Mapping of the parts and relationships of a system
Can involve mapping of a system, key informant interviews, or network analysis
Adapted from: Measuring Up, A Guide for Learners. AIDS Alliance; 2010.

## Slide 18: Example 1
Problem Statement: PLHIV in Malawi denied access to care, treatment, and support
Advocacy Goal: Equal access to high-quality health services for all PLHIV in Malawi
Advocacy Objective: MOH commits to adopting a policy of providing high-quality health services to all PLHIV
Indicator: MOH resolution published by March 2020 on provision of high-quality services for all PLHIV
Activities
1: Analyze data on current quality of health care services for PLHIV
2: Develop briefing paper on current status of care and potential impact of changed policy
Indicator: Briefing paper written on the status and quality of health care services for PLHIV based on current data, and potential impact of changed policy
3: Present data and briefing paper to MOH technical working group at quarterly meeting
Indicator: Presentation developed and delivered to MOH during quarterly meeting
Adapted from: A2 Analysis and Advocacy, Advocacy Training Manual, Health Policy Initiative, 2007.

## Slide 19: Example 2
Problem Statement: Lack of government commitment (policy and resources) to the national HIV and AIDS program, which has limited HIV services for the general population
Advocacy Goal: Adoption of national HIV and AIDS policy and allocation of appropriate resources for its implementation
Advocacy Objective: National AIDS Council (NAC) will draft and submit a National HIV and AIDS Policy and Operational Plan for approval within one year
Indicator: National HIV and AIDS Policy and Operational Plan submitted to MOH for approval
Activities
1: Conduct stakeholder meeting to gather input about activities to include in the plan
Indicator: Draft list of activities developed as a result of stakeholder meeting
2: With research partners, review plans of other countries and develop a briefing note on important considerations for the NAC
3: Develop a website to track commitments by the NAC of what will be included in the plan and progress toward completion
Indicator: Tracking website developed with initial commitments of the NAC
Adapted from: A2 Analysis and Advocacy, Advocacy Training Manual. Health Policy Initiative; 2007.

## Slide 20: Measurement Indicators Handout

## Slide 21: Activity—Drafting Indicators
Develop indicators for your strategies (small groups, 30 minutes):
  1 indicator for the objective
  1 indicator for at least 2 activities
  Consult your handout for guidance to ensure that indicators are suitable.
Identify the data source and individual(s) responsible for collecting data.
Provide justification for selecting each indicator (related to characteristics of good indicators).
Share indicators with the large group.

## Slide 22: Learning Objectives—Session 12
Define methods used to track success and evaluate advocacy
Use logic models as a tool to show progress toward advocacy goals and objectives
Describe methods for evaluating advocacy
Develop indicators for your advocacy strategy